## Feedback Tracker
# | Module | Feedback | Proposed Solution | Priority | Status | Assigned To | Raised Date | ETA | Completion Date | Remarks
1 | PTP Queue | Display number of cases where PTP resolution or update is not done yet. This should be cumulvative number till date | Add a cumulative pending PTP counter on the PTP Queue dashboard showing unresolved cases till date | Medium | Open
2 | PTP Queue | Allow collection officer to update the PTP date. Count of PTP date change should be displayed on the case. This will help understand the PTP broken cases | Enable PTP date edit with a change counter badge on each case; maintain audit log of date changes | Medium | Open
3 | PTP Queue | Visually cues should be added to the PTP listing to understand the cases where PTP has been broken,PTP is yet to come, PTP update is due | Use color-coded tags/icons — Red: PTP Broken, Amber: PTP Update Due, Green: PTP Yet to Come | Medium | Open
4 | PTP Queue | Allow filter using Customer Name | Add a Customer Name search/filter field in the PTP Queue listing filters | Low | Open
5 | Debt Management | DPD Bucket should be diaplyed in the listing of the cases | Add DPD Bucket column in the Debt Management case listing grid | High | Open
6 | Debt Management | Vissually cues should be added to distinguish between Bucket 3, Bucket 2, Bucket 1, NPA and Normalized cases | Apply row-level color coding — Bucket 3: Red, Bucket 2: Orange, Bucket 1: Yellow, NPA: Dark Red, Normalized: Green | Medium | Open
7 | Debt Management | Sorting basis Bucket 3, Bucket 2, Bucket 1, NPA and Normalized cases | Add sort option on DPD Bucket column with predefined sort order: B3 > B2 > B1 > NPA > Normalized | Low | Open
8 | Payment | UAT Sanity should be done for the Payment Link | Execute UAT sanity test suite covering payment link generation, delivery, expiry, and redemption flows | High | Open
9 | Payment | POC should be initiated post sanity at select few locations for payment link | Identify 3-5 pilot locations post UAT sign-off; run controlled POC with defined success metrics | High | Open
10 | Payment | Resend Link should expire the old link | Auto-expire previous active link when a new Resend Link request is triggered | Medium | Open